## Slide 1: WESyS Team Meeting
December 4th, 2019

## Slide 2: Agenda
Finances
AOP and milestone review
Review of roles and responsibilities
Q1 Milestone status
Task timeline for 2020
Other items?

## Slide 3: Finances
FY19 GSO = $24,662 (~ 8%) (this is the unburdened amount; we put added money to the Lexidyne subcontract at the end of FY19)
FY20 approved budget = $300,000
FY20 funds are late and are being parsed out. We have finally received funds ($30,000) in our task.
FY20 planned spending = $268,773
FY20 GSO = $55,889 (~19%)

## Slide 4: AOP and Milestones
Provide model documentation to relevant stakeholders as part of the formation of an external advisory board in Q2. Supporting documentation will be decided on in consultation with DOE and could include a draft methods section for a journal article or a one-page flier that highlights the methods, approach, and capabilities of WESyS. | 12/30/2019 | Quarterly Progress Measure (Regular)
Formation of an external advisory board (targeting up to 10 members) and initial model review webinar. We will contact interested stakeholders from industry, government, and academia to serve as an external advisory board for the WESyS project. This board will provide critical input on modeling approaches, scope, analysis questions, and results. We will use the documentation developed in Q1 to execute an initial model review webinar with the external advisory board by March 30, 2020. | 3/30/2020 | Quarterly Progress Measure (Regular)
Summarizing input received from the first review with the external advisory board, including input on the approach, scope, results, and outcomes. We will also outline next steps identified during the model review. | 6/30/2020 | Annual Milestone (Regular)
Critical model review: Are the analyses and model relevant for BETO and the stakeholder community at large? This decision will be based on the review of our model documentation by BETO. 1) Meets BETO/stakeholder needs; proceed. 2) There are model and data deficiencies; update the model and/or data deficiencies. 3) The model and analysis fail to meet BETO/stakeholder needs; terminate project. | 6/30/2020 | Go/No-Go – does the model useful? For whom? How it reflects the real industry?
Synthesis of the insights gained through sensitivity and scenario analyses performed in FY19. This systhesis will be the basis of a manuscript suitable for submission to a relevant refereed journal. This synthesis will be in the context of providing DOE and the community at large with actionable information. We will provide BETO with a draft manuscript by the end of the quarter. Submission to a suitable journal will be at a later date, likely within the 2020 calendar year. Whether to proceed and the exact date of submission is dependent on NREL and DOE reviews. | 9/30/2020 | Quarterly Progress Measure (Regular)

## Slide 5: Planned hours, roles, and responsibilities
Danny – 272hrs- project management, lead Q1 milestone, contribute to Q2, Q3, Q4 milestones. Lead go/no-go milestone
Laura – 182hrs – lead Q2 and Q3 milestones, contribute to Q1, Q4.
Annika – 636hrs – lead Q4 analysis, contribute to Q1, Q2, Q3 milestones.
Irina – 736hrs – key contributor for Q1 and Q2 milestones –
Q1 – map; Q2 –
Some Q4 – refreshing;
Dylan – 72hrs – database support, potential Q4 support
Melissa – 96hrs – project management support
Lexidyne – ~25K - key contribution to Q1 milestone. Support for Q2 and Q3 milestone.

## Slide 6: Q1 milestone status
Due December 31st - 27 December
Documentation first pass – Steve
  Approach, diagrams, data, how we did it
  Details (прям по костям) – Generic and for details look ap.#
  Module way, reusable structure, the components and their modification
  High level info+ по костям details
  Ну и поиграться с моделью для ощущения реальности (Дэнни)
Model mapping – Irina
List of potential collaborators – Danny/Mark Philbrick
Milestone draft and submission – Danny

## Slide 7: Potential Advisory Board
Anil Prabhu - CARB (*confirmed)
Thomas Frankiewicz – EPA
Robert Hallenback – Waste Management Inc
Leslie Snowden-Swan– HTL person (PNNL)
WRF wat res feder – Mark is looking
CEC ca energy com (renew gs stand) – Mark is looking
Private sector
WEF
American Biogas council
Policy aspect (cl air act)
Waste-to-energy (WRF, Waste Management)
Documentation
Focus group – potential users; documentation for individuals, specific industry, or something even higher. We can use the professionals to inform the inv decision; Answer question – what we are trying to do and to show by using this model?
Way to explain what is the model is?
One approach to documentation - where are the facilities? What are their ? We are interested in scale effect/ policy effect/
As result: Danny will gather the information
Interface: design interface with out audience in mind (for HTL, LF)
Senior people – prefer to explore the model by them and we should be ready to answer the questions of people when they have it
From steve the explanation of the logic
Here is the analysis platform
We can do this this and this
Lets play
Ask the advisory board to do exploration

## Slide 8: FY20 Timeline December
Task | Dec 2 - 6 | Dec 9 – 13 | Dec 16 - 20 | Dec 23 - 27 | Dec 30 - 31
Review draft documentation | All | All |  |  | 
Review draft model mapping | All | All |  |  | 
Draft email to potential external advisors | Danny |  |  |  | 
Short list of potential advisors selected | All | All |  |  | 
Email sent to potential advisors |  | Danny |  |  | 
Comments on draft materials |  | Annika – map Documentation - Laura |  |  | 
Revise draft materials |  |  | Steve - Documentation Irina - map | Steve - Documentation Irina - map | 
Final material review |  |  |  | Danny | Danny
Git Repository for Advisors |  | Danny |  |  | 
Milestone Submission |  |  |  |  | Danny

## Slide 9: FY20 Timeline
Task | Jan | Feb | Mar | April | May | June | July | Aug | Sept
Initial model webinar scoping and draft | All |  |  |  |  |  |  |  | 
Model webinar scheduled |  | All |  |  |  |  |  |  | 
Model webinar |  |  | L,D,S |  |  |  |  |  | 
Milestone submission |  |  | D |  |  |  |  |  | 
Model review planning and draft agenda |  |  | All | All |  |  |  |  | 
Review scheduled |  |  | All |  |  |  |  |  | 
Model review Meeting |  |  |  |  | L,D,S,A |  |  |  | 
Go/No-Go |  |  |  |  | D/BETO |  |  |  | 
Milestone Submission |  |  |  |  | D |  |  |  | 
Creating plots of past sens studies |  |  |  | I, A | I, A |  |  |  | 
Review of past sens studies |  |  |  | I, A | I, A | I, A |  |  | 
Decide on more runs for Q4? |  |  |  |  |  | A, All |  |  | 
Draft manuscript |  |  |  |  |  |  | A, All |  | 
Comments back on manuscript |  |  |  |  |  |  |  | All | 
Manuscript revision |  |  |  |  |  |  |  | A, All | 
Final manuscript for submission as milestone |  |  |  |  |  |  |  |  | D, All
Merit Review |  |  |  |  | D/BETO | D/BETO | D/BETO |  | 
L = Laura, D = Danny, A = Annika, S = Steve, I = Irina